## Parts At ATA
Antenna Inventory | [6 empty] | Antenna Modification and Measurements
Ant | ControlBox | DriveBox | Feed | PaxBox | RFCB | Notes | GND bridge | Measured PAX | H/C Measurement Feed
1A | CB-0016 | DB-016 | SB-017 | PB-012 | RFCB-039
1B | CB-0039 | DB-030 | SB-008 | PB-001 | RFCB-025
1C | CB-0028 | DB-025 | 5C4-019 | PB-040 | RFCB-040 | PB tested and replaced | x | x | x
1D | CB-0042 | DB-008 | SB-028 | PB-024 | RFCB-036
1E | CB-0029 | DB-039 |  |  | RFCB-033 | Feed at Minex for repair, PB is in E-Lab
1F | CB-0138 | DB-027 | SB-039 | PB-022 | RFCB-042
1G | CB-0004 | DB-019 |  | PB-034 | RFCB-038 | no RFCB
1H | CB-0034 | DB-041 | 5C4-013 | PB-039 | RFCB-027
1J | CB-0111 | DB-0034 | - | - | - | no feed, no RFCB
1K | CB-0046 | DB-038 | 5C4-012 | PB-026 | RFCB-029
2A | CB-0006 | DB-020 | 5C4-005 | PB-013 | RFCB-032 |  |  |  | x
2B | CB-0012 | DB-031 | 5C4-004 | PB-005 | RFCB-043 |  |  |  | x
2C | CB-0025 | DB-033 | SB-012 | PB-003 | RFCB-026
2D | CB-0051 | DB-0002 | SB-014 | PB-041 | RFCB-011
2E | CB-0020 | DB-035 | 5c4-016 | PB-029 | RFCB-037 |  | x |  | x
2F | CB-0021 | DB-017 | SB-019 | PB-021 | RFCB-034
2G | CB-0101 | DB-045 | SB-027 | PB-032 | - | no RFCB
2H | CB-0017 | DB-022 | 5C4-018 | PB-006 | RFCB-035 |  | x | x | x
2J | CB-0018 | DB-009 |  | PB-011 | RFCB-013 |  |  |  | x
2K | CB-0044 | DB-032 | SB-016 | PB-014 | RFCB-017
2L | CB-0010 | DB-012 | SB-024 | PB-044 | RFCB-020
2M | CB-0032 | DB-007 |  |  | RFCB-015 | Feed at Minex for repair, PB is in E-Lab
3C | CB-0033 | DB-004 | 5C4-020 | PB-016 | RFCB-048 |  | x | x
3D | CB-0049 | DB-047 |  | PB-002 | RFCB-018 | Feed at Minex for repair, PB is in E-Lab
3E | CB-0003 | DB-011 | SB-003 | PB-035 | RFCB-023
3F | - | - | - | - | - | no feed, needs all three rimbox boards, 24v power supply and power dist board
3G | - | - | - | - | - | no feed
3H | - | - | - | - | - | no feed, needs 24 power supply
3J | CB-0040 | DB-013 | SB-007 |  | RFCB-049
3L | CB-0030 | DB-005 | 5C4-007 | PB-004 | RFCB-046 |  | x |  | x
4E | CB-0136 | DB-0014 | - | - | RFCB-044 | no feed
4F | CB-0113 | DB-0049 | - | - | RFCB-021 | no feed
4G | CB-0043 | DB-037 | SB-030 | PB-037 | RFCB-014
4H | CB-0124 | DB 0006 | - | - | RFCB-022 | no feed, rim box needs 24V supply and power dist board
4J | CB-0019 | DB-010 | 5C4-006 | PB-008 | RFCB-024 |  | x | x | x
4K | CB-0027 | DB-046 | SB-023 |  | RFCB-030
4L | CB-0041 | DB-040 | SB-031 |  | RFCB-041
5B | CB-0031 | DB-043 |  |  | RFCB-012 |  |  |  | x
5C | CB-0100 | DB-018 | SB-038 |  | RFCB-031
5E | CB-0009 | DB-029 | SB-021 |  | RFCB-051
5G | CB-0008 | DB-024 | SB-046 |  | RFCB-019
5H | CB-0114 | DB-028 | SB-033 |  | RFCB-052
Antonio feeds: 1c,1e,1g,1h,1k,2a,2b,2e,2h,2j,2m,3c,3d,3l,4j,5b
* in Notes = Antonio Feed
Mark reports all Rim Boxes are installed and there are enough cards to complete all 42.
Rim Boxes do not have serial numbers, they are not tracked
We have all RFBCs and 2 to spare once repaired at SRI
Parts needed for full operation:
3 - Control Boxes |  | 4 are at SRI | 4 are at ATA
3 - Drive Boxes |  | 2 are at SRI | 4 is at ATA
8 - Pax Boxes |  |  | 9 are at ATA
Spare parts at ATA (main lab):
3 - Control Boxes |  | CB-0135, CB-0050, CB-0126, CB-0138
1 - Drive Box |  | DB-0021, DB-0048, DB-0047, DB-0009

## Feed Retrofit Overview Dates
Feed List |  | Feed Revision Overview
Number | Installed Ant. | Tip-Link: R03 | Temp S. Isolation | New Harness | Bellow Removed | Cryo Tuned | Firmware 5.4 | Gold-Plated | Preconditioned Coax | ETA on Antenna
5C4-002 | Feed Lab |  | 2021-12-02 | 2021-12-02 | 2021-05-02
5C4-003 | Feed Lab (5B) | MINEX | x | x | x | x | x | x | MINEX
5C4-004 | 2B | x | x | x | x | x | x | x | x
5C4-005 | 2A
5C4-006 | 4J | x | x | x | x | x | x | x | x
5C4-007 | Feed Lab |  | 2021-12-02 | 2021-12-02 | 2021-05-02
5C4-008 | Feed Lab (1G) | MINEX | x | x | x | x | x | x | MINEX | 2021-01-02
5C4-009 | Feed Lab |  | 2021-05-02 | 2021-05-02 | 2021-05-02
5C4-010 | Feed Lab | MINEX | x | x | x | x | x | x | MINEX | 2021-01-02
5C4-011 | Feed Lab (3L) | MINEX | x | x | x | x | x | x | MINEX
5C4-012 | 1K | x | x | x | x | x | x | x | NA
5C4-013 | 1H | x | x | x | x | x | x | x | x
5C4-014 | Feed Lab (2J) | MINEX | x | x | x | x | x | x | MINEX
5C4-015 | Feed Lab |  | 2/19/2021 | 2/19/2021 | 2021-05-02
5C4-016 | Feed Lab | x | x | x | x | x | x | x | x
5C4-017 | Feed Lab |  | 2/19/2021 | 2/19/2021 | 2021-05-02
5C4-018 | 2H | x | x | x | x | x | x | x | NA
5C4-019 | 1C |  | x | x | x | x
5C4-020 | 3C | x | x | x | x | x | x | x | x

## Feed Retrofit Overview
Feed List |  | Feed Revision Overview
Number | Installed Ant. | Tip-Link: R03 | Temp S. Isolation | New Harness | Bellow Removed | Cryo Tuned | Firmware 5.4 | Gold-Plated | Preconditioned Coax | Inner Feed / LNAs
5C4-002 | Feed Lab
5C4-003 | Feed Lab |  | x | x | x | x | x | x
5C4-004 | 2B | x | x | x | x | x | x | x | x | (002) 62 / 55
5C4-005 | 2A
5C4-006 | 4J | x | x | x | x | x | x | x | x
5C4-007 | 3L | x | x | x | x | x | x | x | x | (004) 62 / 55
5C4-008 | Feed Lab (1G) |  | x | x | x | x | x
5C4-009 | Feed Lab |  | x | x | x | x | x
5C4-010 | Feed Lab | MINEX | x | x | x | x | x | x | MINEX
5C4-011 | Feed Lab (3L) | MINEX | x | x | x | x | x | x | MINEX
5C4-012 | 1K | x | x | x | x | x | x | x | NA
5C4-013 | 1H | x | x | x | x | x | x | x | x
5C4-014 | Feed Lab (2J) | MINEX | x | x | x | x | x | x | MINEX
5C4-015 | Feed Lab |  | x | x | x | x | x
5C4-016 | 2E | x | x | x | x | x | x | x | x | (007) 85 / 99
5C4-017 | Feed Lab |  | x | x | x | In Progress | In Progress
5C4-018 | 2H | x | x | x | x | x | x | x | NA
5C4-019 | 1C |  | x | x | x | x
5C4-020 | 3C | x | x | x | x | x | x | x | x | (---) 83 / 84

## Vibration Measurements
Feed List |  | Vibration Measurements
Number | Installed Ant. | Initial, before tuning | Tuned Value | Followup measurement
5C4-002 | Feed Lab
5C4-003 | Feed Lab | X=0.20 Y=0.07 Z=0.200 | X=0.05 Y=0.05 Z=0.12
5C4-004 | 2A | X=0.09 Y=0.07 Z=0.260 | X=0.07 Y=0.04 Z=0.16
5C4-005 | 2A
5C4-006 | 4J |  | X=0.15 Y=0.13 Z=0.10
5C4-007 | Feed Lab | X=0.15 Y=0.05 Z=0.38 | X=0.04 Y=0.05 Z=0.11
5C4-008 | Feed Lab (1G) | X=0.19 Y=0.05 Z=0.18 | X=0.09 Y=0.04 Z=0.16
5C4-009 | Minex | X=0.13 Y=0.05 Z=0.14 | X=0.08 Y=0.04 Z=0.15
5C4-010 | Feed Lab (2B) | X=0.120 Y=0.04 Z=0.220 | X=0.08 Y=0.03 Z=0.15
5C4-011 | Feed Lab (3L) | X=0.237 Y=0.053 Z=0.185 | X=0.07 Y=0.05 Z=0.16
5C4-012 | 1K |  | X=0.32 Y=0.09 Z=0.14
5C4-013 | Feed Lab (1H) |  | X=0.12 Y=0.06 Z=0.22
5C4-014 | Feed Lab (2J) | X=0.370 Y=0.08 Z=0.190 | X=0.07 Y=0.03 Z=0.15
5C4-015 | Minex | X=0.13 Y=0.05 Z=0.28 | X=0.07 Y=0.02 Z=0.12
5C4-016 | Minex | X=0.70 Y=0.04 Z=0.130 | X=0.05 Y=0.04 Z=0.14
5C4-017 | Minex
5C4-018 | 2H
5C4-019 | 1C
5C4-020 | 3C

## Parts at SRI
Part serial # | Current Status | Original Complaint Anecdote (if known) | Findings | Action taken
CB-0147 | retained for sw dev |  |  | CB-0047 upgraded to new CB hw/sw, serial number changed
CB-0113 | at HCRO |  |  | upgraded
CB-0126 | at HCRO |  |  | upgraded
CB-0138 | at HCRO |  |  | upgraded
CB-0105 | PCB upgraded, needs sw load and testing
CB-0114 | upgraded, tests OK
CB-0045 | not yet upgraded
DB-0006 | at HCRO | az servo status | No problems seen, alternate filter coeeficients
DB-0014 | at HCRO | "not booting" | ping response visible on fiber but not detected by CB | replaced fiber
DB-0021 | at HCRO | az servo status | Az spontaneously disables, unusual az Accelnet errors | Replaced az Accelnet module
DB-0047 | at HCRO | "az moving back and forth" | No problems seen, has older firmware
DB-0003 | retained for SW dev | "servos won't reset and stay reset" | El Accelnet module is physically damaged and unresponsive. drivebox probably dropped. Fiber crimped, dim. | Replaced El Accelnet module and configured it. Replaced fiber
DB-0004 | at HCRO | az servo status | No problems seen, alternate filter coeeficients
DB-0005 | at HCRO | "el servo resets" | No problems seen, missing usual serial number label | Relabelled from ADB0016 to DB-0049
DB-0006 | at HCRO | Accelnet modules and daughterboard replaced but no operation | Both Accelnet modules were unconfigured. Emitters brighter than most | Configuration copied from DB-0047, now functional.
DB-0009 | at HCRO
DB-0002 | at HCRO | Invalid return from servos, az brake cycling, ticking sound from motors |  | Replaced and programmed both az/el Accelnet modules
RB-??? | unknown, brought to SRI to study for designing replacement rimbox PCB/SBC
focus motor | unknown, brought to SRI to study for designing replacement rimbox PCB/SBC
RFCB-55 | at HCRO
RFCB-56 | at HCRO
RFCB-016 | unknown
RFCB-028 | unknown
RFCB-045 | unknown
RFCB-047 | unknown
RFCB-050 | unknown
RFCB-053 | unknown
RFCB-054 | unknown

## Parts at Minex
Feeds Being Repaired
Original Dish | Feed SN
1c | 5C4-007
1e | 5C4-002
2h | 5C4-009
2m | 5C4-015
3d | 5C4-017
3c | 5C4-016
LNAs outside of feeds
From 006 | sn0050A | OK
From 006 | sn0071A | OK
From 007 | sn0030A
From 007 | sn0068A
From 016 | sn0021A | run wet, 6 month with ice
from 016 | sn0019A | run wet, 6 month with ice
unknown | sn0013A | single LNA possible working
unknown | sn0061A | broken wirebond
LNAs inside feeds
In feed 020 | sn0083A | ok
In feed 020 | sn0084A | ok
In feed 019 | sn0034A | ok
In feed 019 | sn0046A | ok
In feed 006 | sn0075A
In feed 006 | sn0082A
In feed 002 | sn0055A | at Minex
In feed 002 | sn0062A | at Minex
In feed 007 | sn0085A | at Minex
In feed 007 | sn0099A | at Minex
In feed 017 | sn0024A | at Minex
In feed 017 | sn0073A | at Minex
Feeds without LNA
Feed 009
Feed 015

## Parts at SSL
Original Dish | Feed SN
Feed Stand

## PAX Boxes
PAX Box Number | Original Feed | Feed information source | Current Location | Status | Comments
PB-001 | 1B | Pulled out and recorded & feed parts spreadsheet | Lab 1 | Calibrated | A little bit of bumpiness in both passbands
PB-002 | 3D | Feed parts spreadsheet | Missing (possibly at Minex)
PB-003 | 2C | Pulled out and recorded & feed parts spreadsheet | Lab 1 | Needs testing | Y passband not ideal
PB-004 | 5H | Feed parts spreadsheet | Lab 1 | Calibrated
PB-005 | 2B | Feed parts spreadsheet | 2B | Calibrated and inside working feed
PB-006 | 2H | Feed parts spreadsheet | 2H | Calibrated and inside working feed
PB-007 | Unknown | Not listed in feed parts spreadsheet | Workshop | Missing a control board | Not in working condition
PB-008 | 3L | Feed parts spreadsheet | Lab 1 | Calibrated
PB-009 | 3C | Feed parts spreadsheet | Workshop | Calibrated | Passbands are a bit bumpy
PB-010 | Unknown | Not listed in feed parts spreadsheet | Lab 1 | Calibrated | Control board was replaced with PAX 17’s & passbands are bumpy
PB-011 | 2J | Feed parts spreadsheet | Lab 1 | Calibrated (maybe needs fixing) | Issue with X-Pol fiber or board causing X passband to be ugly
PB-012 | 1A | Feed parts spreadsheet | Missing (possibly at Minex) | Calibrated (it was calibrated in February according to measurement file)
PB-013 | 2A | Feed parts spreadsheet | 2A | Calibrated and inside working feed | Y detectors saturate at 1.7dBm on noise measurement & has a bumpy passband
PB-014 | 2K | Pulled out and recorded & feed parts spreadsheet | Lab 1 | Calibrated
PB-015 | Unknown | Not listed in feed parts spreadsheet | Lab 1 | Calibrated | Bumpy X passband
PB-016 | 5E | Feed parts spreadsheet | Lab 2 | Calibrated | X saturates at 1.7dbm for both x measurements. Bumpy passbands
PB-017 | 4J | Feed parts spreadsheet & piece of tape on box | Workshop | Missing a control board | Not in working condition
PB-018 | Unknown | Not listed in feed parts spreadsheet | Unknown if it actually exists
PB-019 | 5G | Feed parts spreadsheet | Lab 1 | Calibrated | X saturates at 1.7dbm for both x measurements. Bumpy passbands
PB-020 | Unknown | Not listed in feed parts spreadsheet | Minex
PB-021 | 2F | Pulled out and recorded & feed parts spreadsheet | Workshop | Missing both PAMs | Not in working condition
PB-022 | 1F | Feed parts spreadsheet | 1F | Calibrated and inside working feed | Detectors saturate at 1.8dBm for both x&y on noise measurements
PB-023 | Unknown | Not listed in feed parts spreadsheet | Unknown if it actually exists
PB-024 | 1D | Pulled out and recorded & feed parts spreadsheet | Lab 1 | Calibrated | Y detector saturate at 1.5dBm on noise measurement & bumpy passbands
PB-025 | Unknown | Not listed in feed parts spreadsheet | Lab 1 | Calibrated (maybe needs fixing) | Low X gain (maybe broken amplifier)
PB-026 | 1K | Feed parts spreadsheet | 1K | Calibrated and inside working feed
PB-027 | 3J | Pulled out and recorded & feed parts spreadsheet | Workshop | Calibrated (maybe needs fixing) | Bowl shaped Y passband so filter or slope supporter possibly broken
PB-028 | Unknown | Not listed in feed parts spreadsheet | Lab 1 | Calibrated (maybe needs fixing) | Y saturates at 1dBm on noise measurement & bowl shape passbands (broken filter or slope supporter maybe)
PB-029 | 2E | Feed parts spreadsheet | Lab 1 | Calibrated | Y passband and power sweep are both unusual
PB-030 | Unknown | Not listed in feed parts spreadsheet | Lab 1 | Calibrated | X passband is 10dBm less than Y’s
PB-031 | 5C | Feed parts spreadsheet | 5C | Calibrated and inside working feed | Low Gain on X-Pol, looks like fiber link
PB-032 | 2G | Pulled out and recorded & feed parts spreadsheet | Workshop |  | Y passband indicates there is filter or slope supporter broken
PB-033 | 4L | Pulled out and recorded & feed parts spreadsheet | Lab 1 | Calibrated
PB-034 | 1G | Feed parts spreadsheet | Lab 1 | Calibrated | Bumpy X passband
PB-035 | 3E | Pulled out and recorded & feed parts spreadsheet | Lab 1 | Calibrated | Bumpy and sloping X passband
PB-036 | Unknown | Not listed in feed parts spreadsheet | Unknown if it actually exists
PB-037 | 4G | Feed parts spreadsheet | 4G | Calibrated and inside working feed | Dip in passband of X-Pol
PB-038 | Unknown | Not listed in feed parts spreadsheet | Lab 1 | Calibrated | Control board replaced with PAX 7’s & bumpy Y passband
PB-039 | 1H | Feed parts spreadsheet | Lab 1 | Calibrated
PB-040 | 1C | Feed parts spreadsheet | 1C | Calibrated and inside working feed | Possible problem with temp stabilization & bumpy passbands
PB-041 | 2D | Pulled out and recorded & feed parts spreadsheet | Workshop | Missing both PAMs | Not in working condition
PB-042 | 4K | Pulled out and recorded & feed parts spreadsheet | Lab 1 | Calibrated
PB-043 | Unknown | Not listed in feed parts spreadsheet | Lab 1 | Calibrated
PB-044 | 2L | Pulled out and recorded & feed parts spreadsheet | Lab 1 | Calibrated | Bumpy passbands
PB-045 | 5B | Feed parts spreadsheet | Lab 1 | Calibrated | Bumpy X passband